## Delivery Roadmap
FTF AGENTIC AI OPERATING SYSTEM
Agile Delivery Roadmap — What You Receive at Each Stage
Every sprint delivers a working, testable piece of the system. Nothing is released until it works. You test each piece before the next one begins.
Sprint | Week | Theme — What Gets Built | What You Receive | How to Test It | Your Action Required | Phase | Status
Sprint 0 | Week 1 | Foundation & Connections VPS, database, GitHub repo, all 5 API connections tested and verified | • API connectivity report — confirms all 5 systems can talk to each other • Staging environment accessible to the team • Project repository live on GitHub | • Log in to staging FTF • Confirm test data visible • Review API connection report | ✅ Confirm staging environment has test orders, customers, and invoices | Phase 0 Foundation | Pending
Sprint 1 | Week 2 | Order Detection AI monitors FTF every 60 minutes and finds new unprocessed orders automatically | • Live demo — AI detects new orders in staging FTF within 60 min • Order detection log showing every order the AI found • Database showing orders queued for processing | • Submit 3 test orders in staging FTF at different times • Confirm AI detects all 3 within 60 min • Check detection log is accurate | ✅ Submit 3 test orders in staging ✅ Confirm AI found each one | Phase 1 Loop 1 | Pending
Sprint 2 | Week 3 | Smart Classification AI reads every order and identifies: customer type (individual vs B2B), FEMA flood zone, pricing tier, and any special conditions | • Classification report for each test order — shows exactly what AI identified • FEMA flood zone detection working — auto-adds Elevation Certificate if needed • Proof that B2B and individual orders are treated differently | • Submit: 1 individual order, 1 B2B order, 1 property in a FEMA flood zone • Review classification report for each • Confirm FEMA detection correctly adds Elevation Certificate | ✅ Robert / Mark: submit 5 different order types and verify classifications are correct ✅ Flag any misclassified orders back to Prateek | Phase 1 Loop 1 | Pending
Sprint 3 | Week 4 | Flag Detection & Human Gate AI applies all 8 flag rules — automatically routes unusual orders to your team via MS Teams before any estimate is sent | • Live MS Teams alert demo — competitor order triggers an immediate team notification • Flag trigger working for all 8 rules: competitor, ALTA Table A, Other Services, new customer, etc. • Proof that no flagged order goes out automatically | • Submit a competitor company order • Submit an ALTA Table A Survey order • Submit an 'Other Services' order • Confirm all 3 trigger MS Teams alerts before any estimate is generated | ✅ Robert / Mark: provide final competitor company names list so flags are accurate ✅ Confirm MS Teams alerts are received on your devices | Phase 1 Loop 1 | Pending
Sprint 4 | Week 5 | Pricing Engine AI looks up the correct price for every survey service — uses custom client rates first, then the master price sheet | • Pricing accuracy test — AI prices 24 service types correctly against the master sheet • Special pricing overrides verified — clients with custom rates get their correct price • Pricing report for Robert / Mark to review and sign off | • Submit an order for 10 different survey types • Confirm each is priced correctly against the master sheet • Submit 1 order from a client with a custom rate — confirm override applies | ✅ Ryan: approve master pricing sheet in SalesFlow before this sprint ✅ Robert / Mark: review pricing test report and confirm accuracy | Phase 1 Loop 1 | Pending
Sprint 5 | Week 6 | Estimate Writer + Change Order Clause AI writes personalised estimate emails — correct tone for individual vs B2B — with change order clause automatically at the bottom of every estimate | • 5 sample estimate emails for your review • Individual estimate (friendly tone) + B2B estimate (professional tone) • Change order clause visible and correctly formatted on every estimate | • Read each sample estimate • Confirm tone is right for the customer type • Confirm change order clause is present, readable, and professionally worded | ✅ Ryan: provide approved change order clause text BEFORE this sprint begins ✅ Ryan + Robert / Mark: review and approve all 5 sample estimates before Sprint 6 starts | Phase 1 Loop 1 | Pending
Sprint 6 | Week 7 | Quality Control — Reviewer AI reviews its own estimate before sending — checks pricing, customer details, and that the change order clause is present. Up to 3 self-correction loops. | • Demo of AI catching its own mistake and self-correcting (no human needed) • Reviewer test report — all checks passing: price ✓, name ✓, address ✓, clause ✓ • Confirmation that no estimate with an error can be sent | • Review the reviewer test report • Check that all 4 reviewer checks are passing • Confirm self-correction loop demo makes sense | ✅ Review the demo and confirm quality control standard is acceptable | Phase 1 Loop 1 | Pending
Sprint 7 | Week 8 | 🎯 MILESTONE — Full Estimate Loop Live First complete end-to-end estimate: order submitted → AI detects → classifies → prices → writes → reviews → sends — with 6-13 minute human-feel delay | 🎯 FIRST LIVE TEST ESTIMATE sent to Ryan's email from staging FTF • Full loop running on staging — all 7 agents connected • Daily MS Teams digest showing what AI did • Go / No-Go decision point before production | • Submit 1 test order in staging FTF • Wait up to 75 minutes • Receive the test estimate in your inbox • Review: is it correct? Does it look professional? Is the clause present? | ✅ Ryan + Robert / Mark: review the live test estimate ✅ Give go / no-go decision for Phase 2 (staging testing) ✅ Report any issues to Prateek within 48 hours | Phase 1 Loop 1 | Pending
Sprint 8 | Week 9 | Full Staging Test + Cost Report Complete Loop 1 tested on staging with 10+ different order types. Credit usage benchmarked. Cost report prepared for Ryan's approval. | • Full staging test results — 10 different order types, all working • Monthly AI running cost estimate (in dollars) • Go / No-Go decision pack for production • Reporter daily digest sample | • Submit 10+ orders of different types across 3 days • Confirm all estimates arrive correctly • Review cost report — is the ongoing cost acceptable? | ✅ Ryan: review and approve the monthly AI cost before production is activated ✅ All stakeholders: attend or watch staging demo recording | Phase 2 Stage Test | Pending
Sprint 9 | Week 10 | AR Follow-Up Loop AI scans FTF Books daily for unpaid invoices and sends personalised payment reminders — tone automatically adjusts based on how overdue the invoice is | • Demo of reminder cycle on test invoices: friendly → firm → urgent • Jessica receives a test reminder at each stage for her review • 90-day escalation alert visible in MS Teams | • Create 3 test unpaid invoices at different overdue stages • Confirm AI sends the right reminder tone for each • Confirm 90-day invoice triggers MS Teams escalation to Ryan | ✅ Jessica: review reminder tone and schedule — approve or request changes ✅ Jessica: provide list of any clients who should NOT receive automated reminders | Phase 1 Loop 2 | Pending
Sprint 10 | Week 11 | Monthly Statement Loop AI generates a complete billing statement for every B2B client on the 1st of each month — sends Excel + PDF via MS Teams and email | • Sample monthly statement for a test B2B client — Wyatt and Jessica review • Statement delivered via MS Teams with Excel and PDF attached • Confirmation of billing contact logic (master email or order email) | • Review sample statement format • Confirm all orders are listed correctly • Confirm it arrives in MS Teams as expected • Confirm the Excel and PDF attachments open correctly | ✅ Wyatt + Jessica: review and approve monthly statement format before Sprint 11 ✅ Confirm billing contact details for each major title company | Phase 1 Loop 3 | Pending
Sprint 11 | Week 12 | 🎯 MILESTONE — Complete System on Staging All 3 loops + memory loop running together on staging. Full system demo for all stakeholders. Final sign-off before production. | 🎯 FULL SYSTEM LIVE DEMO — all 3 loops running simultaneously on staging • Estimate generation loop + AR loop + monthly statement loop all active • Memory and dream loop logging all activity • Final staging sign-off document for stakeholders | • Attend or watch the full system demo • Submit orders, check estimates, verify reminders, confirm statements • Confirm everything works as expected across all 3 loops | ✅ ALL STAKEHOLDERS: sign off on staging demo ✅ Ryan: give final go-ahead for limited production launch | Phase 2 Full System | Pending
Sprint 12 | Week 13 | 🚀 Limited Production Launch Estimate generation loop goes LIVE on real FTF. Survey orders only. Team monitors alongside the AI for 1 week before full launch. | 🚀 FIRST REAL ESTIMATES sent to real customers from live FTF • AI handling real orders autonomously — team monitors alongside • Daily MS Teams digest showing every estimate sent • Any issues flagged immediately — Prateek on standby | • Monitor the first 5 real estimates sent by the AI • Compare against what you would have sent manually • Report any issues or improvements within 24 hours | ✅ Robert / Mark: monitor the first week of real estimates ✅ Report any quality issues to Prateek immediately ✅ Ryan: confirm go-ahead for full production after 5-day observation | Phase 3 Ltd. Prod. | Pending
Sprint 13 | Week 14 | 🚀 Full Production Launch All 3 loops live on production FTF. AI runs fully autonomously 24/7. UptimeRobot monitoring. Team receives daily MS Teams digest. | 🚀 FULLY OPERATIONAL AI SYSTEM — all 3 loops running live, 24/7 • Estimates delivered within 60 minutes of every order • AR reminders running daily • Monthly statements on 1st of each month • Daily digest to Ryan, Robert/Mark, Jessica, Wyatt via MS Teams | • Observe for 5 business days • Confirm estimates are accurate, timely, and professional • Confirm AR reminders are sending correctly • Confirm system is running autonomously without manual intervention | ✅ Ryan: final production sign-off and acceptance ✅ Team: continue monitoring for 30 days — report any edge cases ✅ Phase 2 (POF + NGE) planning begins | Phase 4 Full Prod. | Pending
Milestone sprints (highlighted gold) are key decision points. Ryan must give go/no-go before the next phase begins. · Phase 2 (POF + NGE replication) begins after Sprint 13 is stable for 30 days.

## Client Testing Checklist
FTF AGENTIC AI OS — CLIENT TESTING CHECKLIST
Complete this checklist at the end of each sprint. Tick every item before sign-off. If anything fails, note it in the 'Notes' column and send to Prateek.
Sprint | What to Check | How to Do It | Pass / Fail | Notes / Issues
Sprint 0 | Can you access the staging FTF environment? | Log into stage.fieldtofinish.jobs | ☐ Pass ☐ Fail
Sprint 0 | Do you see test orders in staging? | Check the orders list in staging FTF | ☐ Pass ☐ Fail
Sprint 0 | Has Prateek shared the API connectivity report? | Review the PDF report sent by Prateek | ☐ Pass ☐ Fail
Sprint 1 | Did the AI detect your test orders within 60 minutes? | Submit 3 orders at different times. Check detection log. | ☐ Pass ☐ Fail
Sprint 1 | Is the detection log showing the correct order IDs? | Compare log entries to the orders you submitted | ☐ Pass ☐ Fail
Sprint 2 | Is an individual order classified as 'individual'? | Submit a personal order. Check classification report. | ☐ Pass ☐ Fail
Sprint 2 | Is a B2B order classified as 'b2b'? | Submit a title company order. Check classification report. | ☐ Pass ☐ Fail
Sprint 2 | Does a flood zone property trigger Elevation Certificate? | Submit an order for a FEMA Zone A property. Confirm EC added. | ☐ Pass ☐ Fail
Sprint 3 | Does a competitor order trigger an MS Teams alert? | Submit an order from a competitor company name. Check Teams. | ☐ Pass ☐ Fail
Sprint 3 | Does an ALTA Table A Survey trigger a Teams alert? | Submit an ALTA order. Confirm flagged before any estimate is generated. | ☐ Pass ☐ Fail
Sprint 3 | Does an 'Other Services' order get flagged? | Submit an Other Services order. Confirm flagged. | ☐ Pass ☐ Fail
Sprint 4 | Is the Boundary Survey price correct? | Submit a boundary survey. Confirm price = $350 (or custom rate). | ☐ Pass ☐ Fail
Sprint 4 | Is a client with a custom rate priced at their override? | Submit an order from a client with a special rate. Confirm override price. | ☐ Pass ☐ Fail
Sprint 4 | Has Robert / Mark reviewed and approved the pricing report? | Robert/Mark sign off on the full pricing test report. | ☐ Pass ☐ Fail
Sprint 5 | Does the individual estimate have the right tone? | Read sample estimate 1. Is it warm and clear for an individual? | ☐ Pass ☐ Fail
Sprint 5 | Does the B2B estimate have the right professional tone? | Read sample estimate 2. Is it more formal and professional? | ☐ Pass ☐ Fail
Sprint 5 | Is the change order clause present on every estimate? | Check the bottom of each of the 5 sample estimates. | ☐ Pass ☐ Fail
Sprint 5 | Has Ryan approved the change order clause wording? | Ryan signs off on the exact wording of the change order clause. | ☐ Pass ☐ Fail
Sprint 6 | Does the reviewer catch a pricing error and self-correct? | Watch the reviewer demo Prateek sends. | ☐ Pass ☐ Fail
Sprint 6 | Does every estimate pass all 4 reviewer checks? | Review the reviewer test report — all 4 checks must show PASS. | ☐ Pass ☐ Fail
Sprint 7 🎯 | Did you receive a test estimate in your email from staging FTF? | Check Ryan's inbox. Estimate should arrive within 75 min of the test order. | ☐ Pass ☐ Fail
Sprint 7 🎯 | Is the pricing correct on the live test estimate? | Compare the estimate price to the master price sheet. | ☐ Pass ☐ Fail
Sprint 7 🎯 | Is the change order clause on the live test estimate? | Scroll to the bottom of the estimate email. | ☐ Pass ☐ Fail
Sprint 7 🎯 | Did you receive the daily digest in MS Teams? | Check your Teams channel for the AI's daily activity report. | ☐ Pass ☐ Fail
Sprint 7 🎯 | Go / No-Go: approved for Phase 2 staging test? | Ryan signs the go/no-go decision. | ☐ Pass ☐ Fail
Sprint 8 | Did all 10+ test orders produce correct estimates? | Review the staging test report Prateek sends. | ☐ Pass ☐ Fail
Sprint 8 | Has Ryan reviewed and approved the monthly AI cost? | Ryan reviews cost report and confirms budget is acceptable. | ☐ Pass ☐ Fail
Sprint 9 | Does a 5-days-before reminder have the right friendly tone? | Jessica reads the test reminder. Is the tone correct? | ☐ Pass ☐ Fail
Sprint 9 | Does a post-due-date reminder have the right urgent tone? | Jessica reads the overdue reminder. Is the urgency appropriate? | ☐ Pass ☐ Fail
Sprint 9 | Does a 90-day overdue invoice trigger Ryan's escalation alert? | Check MS Teams for the escalation notification. | ☐ Pass ☐ Fail
Sprint 10 | Does the monthly statement include all test orders? | Check sample statement against the test invoices in FTF Books. | ☐ Pass ☐ Fail
Sprint 10 | Did the statement arrive via MS Teams with Excel + PDF? | Check Teams. Open both the Excel and PDF attachments. | ☐ Pass ☐ Fail
Sprint 10 | Has Wyatt approved the statement format? | Wyatt signs off on the sample monthly statement. | ☐ Pass ☐ Fail
Sprint 11 🎯 | Did all 3 loops run correctly in the full system demo? | Attend or watch the full staging demo recording. | ☐ Pass ☐ Fail
Sprint 11 🎯 | Have all stakeholders signed off on the staging demo? | Ryan, Robert/Mark, Jessica, Wyatt all confirm. | ☐ Pass ☐ Fail
Sprint 11 🎯 | Go / No-Go: approved for limited production? | Ryan signs the production go-ahead. | ☐ Pass ☐ Fail
Sprint 12 🚀 | Did the first real estimate reach a real customer? | Monitor the first estimate sent from live FTF. | ☐ Pass ☐ Fail
Sprint 12 🚀 | Is the pricing on the live estimate correct? | Robert / Mark compare estimate to what they would have sent. | ☐ Pass ☐ Fail
Sprint 12 🚀 | Did the AI handle the first 5 orders without errors? | Review first 5 estimates in the daily MS Teams digest. | ☐ Pass ☐ Fail
Sprint 13 🚀 | Is the AI running all 3 loops without manual intervention? | Check MS Teams digest over 5 business days. | ☐ Pass ☐ Fail
Sprint 13 🚀 | Are estimates consistently arriving within 60 minutes? | Monitor order-to-estimate time over first week. | ☐ Pass ☐ Fail
Sprint 13 🚀 | Final acceptance sign-off | Ryan signs the final production acceptance document. | ☐ Pass ☐ Fail
Send completed checklist back to Prateek at the end of each sprint. Any failed item blocks the next sprint from starting.

## Who Does What
FTF AGENTIC AI OS — WHO DOES WHAT IN EACH SPRINT
Use this sheet to know exactly what each person needs to do — and when — to keep the delivery on schedule.
Sprint / Week | Ryan | Robert / Mark | Jessica | Wyatt | Dev Team
Sprint 0 Week 1 | Confirm all API keys handed to Prateek | No action | No action | No action | Provide all API credentials Confirm staging test data is ready
Sprint 1 Week 2 | Review detection log | Submit 3 test orders in staging | No action | No action | Confirm FTF staging is accessible
Sprint 2 Week 3 | No action | Submit 5 different order types Review classification report Flag any wrong classifications | No action | No action | Confirm FEMA lat/lng fields in order response
Sprint 3 Week 4 | No action | Submit competitor + ALTA + Other Services orders Provide FINAL competitor company names list | No action | No action | Confirm MS Teams webhook is working
Sprint 4 Week 5 | ✅ CRITICAL: Approve master pricing sheet in SalesFlow BEFORE this sprint | Review and sign off on pricing test report Confirm all 24 service prices are correct | No action | No action | Confirm pricing_master table is live on staging
Sprint 5 Week 6 | ✅ CRITICAL: Provide approved change order clause text BEFORE this sprint Review and approve 5 sample estimates | Review and approve 5 sample estimates Confirm estimate tone and format | No action | No action | Confirm FTF Books estimate supports footer field
Sprint 6 Week 7 | No action | Review reviewer test report Confirm quality control standard is acceptable | No action | No action | No action
Sprint 7 Week 8 🎯 MILESTONE | ✅ Receive and review live test estimate ✅ Give Go / No-Go for Phase 2 | Review the live test estimate Report any issues within 48 hours | No action | No action | Ensure FTF Books payment email is restored
Sprint 8 Week 9 | ✅ Review and approve monthly AI cost Approve budget for production | Review full staging test report | No action | No action | Ensure staging mirrors production
Sprint 9 Week 10 | No action | No action | ✅ Attend AR demo Review reminder tone at each stage Approve or request changes Provide client exclusion list | No action | No action
Sprint 10 Week 11 | No action | No action | ✅ Attend statement demo Review statement format | ✅ Attend statement demo Approve monthly statement format | No action
Sprint 11 Week 12 🎯 MILESTONE | ✅ Attend or watch full system demo ✅ Give final Go / No-Go for production | ✅ Attend or watch full system demo Confirm all issues are resolved | ✅ Attend or watch full system demo | ✅ Attend or watch full system demo | On standby for any last-minute fixes
Sprint 12 Week 13 🚀 LAUNCH | Monitor first 5 live estimates Give go/no-go for full production | ✅ Monitor every real estimate Report any quality issues immediately | Monitor AR reminders | No action | On standby for live support
Sprint 13 Week 14 🚀 FULL LIVE | ✅ Final production sign-off Begin planning Phase 2 (POF + NGE) | Continue monitoring for 30 days | Monitor AR loop daily | Monitor monthly statements | No action
Rows highlighted in amber = this stakeholder has a critical action this sprint. Milestones (gold) require Ryan's explicit sign-off before the next sprint begins.