## 📊 Dashboard
NexGen FTF — Agentic AI OS ¦ Pipeline Report
Generated: May 27, 2026 ¦ Prod DB: nexgen_ftf_db ¦ 1-yr analysis: May 2025 – May 2026
Total Invoiced (1yr) | Orders Billed | AR Outstanding | Avg Invoice | Closed Issues
$13.2M | 18,497 | $6.56M | $565 | 52
SPRINT STATUS
Sprint | Focus | Status | Key Deliverable | Notes
Sprint 0 | Foundation | ✅ RELEASED | DB schema, config, logger
Sprint 1 | Monitor | ✅ RELEASED | Agent 02 — FTF Quote monitor
Sprint 2 | Classifier | ✅ RELEASED | Agent 03 — 50+ alias map, LLM fallback | Prod data expanded aliases 2026-05-27
Sprint 3 | Human Gate | ✅ RELEASED | Agent 04 — batch approval digest
Sprint 4 | Pricing | ✅ RELEASED | Agent 05 — county pricing matrix | Updated with prod actuals
Sprint 5 | Writer + Email | ✅ RELEASED | Agent 06 + 12 — estimate writer, email monitor
Sprint 6 | Reviewer + AR | ✅ RELEASED | Agent 07 + 10 — reviewer, AR scanner
Sprint 7 | AR Escalation | ✅ RELEASED | Agent 11 — 30/60/90 day AR escalation
Sprint 8 | Billing Report | ✅ RELEASED | Agent 09 — monthly billing statement
Sprint 9 | Orchestrator + Memory | ✅ RELEASED | Agent 01 + 13 — orchestrator, pricing trainer
Sprint 10 | Staging QA | 🔄 IN PROGRESS | E2E test runner, QA scenarios (10 orders) | Prateek Test 1 & 2 seeded
Sprint 11 | Prod Hardening | ⏳ PLANNED | Rate limiting, prompt caching, prod go-live | I-019 (caching), I-017 (rate limit)
OPEN ISSUES SUMMARY
ID | Sprint | Severity | Title | Status
I-050 | Sprint 2 | CRITICAL | `property_state` from FTF API returns "FLORIDA" but SERVICE_STATE = "FL" — every FL order falsely flagged as out-of-state | CLOSED
I-051 | Sprint 2 | CRITICAL | Non-standard service types ("Land Survey Only", "Re-survey") pass through classifier unhandled — Pricing Engine fails with PricingError | CLOSED
I-052 | Sprint 2 | MAJOR | Building Stakeout orders not flagged — I-042 mandates human review but not implemented in code | CLOSED
I-053 | Sprint 2 | MAJOR | LLM classifier never enabled — classifier.txt stub unchanged since Sprint 2; Sprint 3 enrichment target missed | CLOSED
I-054 | Sprint 2 | MAJOR | NEVER_AUTO_QUOTE has 3 AI-added entries not confirmed by Robert — may be over-blocking auto-quotes | CLOSED
I-055 | Sprint 2 | MAJOR | B-II Title Review contradiction — I-004 (closed) says auto-quoteable; Robert (Recording 1) explicitly says human review required | CLOSED
I-056 | Sprint 3 | MAJOR | Teams approval buttons (potentialAction) empty — Robert/Mark have no UI to approve/reject from Teams; CLI-only is not production viable | CLOSED
I-057 | Sprint 2 | MAJOR | FTF `/pricing/overrides` endpoint not confirmed in API documentation — special_pricing orders may fail in staging | CLOSED
I-058 | Sprint 10 | MAJOR | No E2E integration test exists — all tests are unit tests with mocked dependencies | CLOSED
I-045 | Sprint 2 | MAJOR | Recording 02 Q1 — Full service type list in Generate Invoice dropdown not captured | OPEN
I-046 | Sprint 9 | MINOR | Recording 02 Q2 — All Track Flow order status values not fully confirmed | OPEN
I-047 | Sprint 5 | MAJOR | Recording 02 Q3 — County-specific pricing matrix undefined | CLOSED
I-048 | Sprint 3 | MAJOR | Recording 02 Q4 — "Smith Zone" yellow flag rule undefined | CLOSED
I-049 | Sprint 6 | MINOR | Recording 02 Q12 — No SLA defined for quote turnaround | OPEN
I-040 | Sprint 11 | MAJOR | 8 mid-pipeline order statuses not filterable via FTF API — On Hold, In-Field, Drafting Queue, etc. | CLOSED
I-041 | Sprint 2 | MAJOR | Competitor list pending — Robert confirmed it exists and will write it up | CLOSED
I-042 | Sprint 3 | MAJOR | Building Stakeout ambiguous — NGE "dabbling" in it again; treat as flag-for-human-review | CLOSED
I-043 | Sprint 6 | HIGH | Change order clause text needed — Ryan to draft; confirmed no existing text in estimates | CLOSED
I-006 | Sprint 7 | CRITICAL | Jessica recording (Recording 10) not yet conducted | CLOSED
I-007 | Sprint 8 | CRITICAL | Wyatt recording (Recording 11) not yet conducted | CLOSED
I-018 | Sprint 6 | MINOR | PII masking in logger.py covers email addresses only — phone numbers, property addresses, customer names logged in plain text | CLOSED
I-019 | Sprint 10 | MINOR | No prompt caching in claude_client.py — cost risk at scale with 7000+ Quote orders | OPEN
I-028 | Sprint 7 | MINOR | Agent 5 Reviewer must log both pre-correction and post-correction estimate for Sprint 7 demo | OPEN
I-032 | Sprint 8 | MAJOR | Recording 11 prerequisites — draft template + Excel vs PDF spec needed before recording | CLOSED
I-059 | Demo | MINOR | Demo narration: "50 new orders a week" too specific — change to "a lot of orders a week" for any client audience | CLOSED
I-060 | Demo | MINOR | Demo classify scene: "no competitor" text not explained — viewers confused why competitor is checked | CLOSED
I-061 | Sprint 5 | MAJOR | New agent required: monitor info@nexgensurveying.com for customer quote-approval emails → move quote to pending | CLOSED
I-062 | Sprint 6 | MAJOR | New feature: website chat → order conversion — customer says "go ahead" → AI asks address or order# → converts quote to pending | OPEN
I-063 | Sprint 7 | CRITICAL | Hard rule: refund requests must NEVER be processed by AI — always route to Jessica immediately, no further action | CLOSED
I-064 | Sprint 3 | MAJOR | Robert approval flow: hourly batch spreadsheet with Approve/Deny column — not per-order Teams ping | CLOSED
I-065 | Sprint 4 | MAJOR | Dynamic pricing factors not in current model: pools, wall count, sheds, driveways, distance from crew | CLOSED
I-066 | Sprint 5 | MAJOR | Historical invoicing: last 2 years of FTF invoice data needed as AI pricing reference | CLOSED
I-067 | Sprint 6 | MAJOR | AI training interface: Robert can describe jobs → AI stores pricing rationale for ongoing learning | CLOSED
I-068 | Sprint 5 | MAJOR | Florida PSM standards: feed FL Professional Surveyor and Mapper standards (Chapter 5J-17 FAC) to AI knowledge base | CLOSED
I-069 | Sprint 6 | MAJOR | Role-based AI modification: Jessica controls AR/refund rules, Robert controls pricing/logistics — cross-domain changes require both | CLOSED
I-070 | Future | MINOR | Weather monitoring agent: daily check → identify survey orders at risk of delay → draft proactive customer emails | OPEN
I-071 | Sprint 2 | MAJOR | "Table Survey" service type in FTF order form UI has no confirmed canonical mapping — will fall through to LLM normalization and may be misclassified | OPEN
I-072 | Sprint 2 | MINOR | "Elevation Code Only" UI label not in alias map — correctly maps to "Elevation Only" canonical | CLOSED
I-073 | Sprint 2 | MAJOR | FTF supports multiple child services per parent order — pipeline treats service_type as single value; multi-service orders may lose child services | OPEN
I-074 | Sprint 10 | MINOR | FTF API has no POST /customers endpoint — programmatic customer creation not possible; QA tests must use pre-existing customer_id | OPEN

## 🐛 Issues
Issue Tracker — FTF Agentic AI OS
OPEN ISSUES (40)
ID | Sprint | Severity | Title | Assigned | Status | Opened | Notes
I-050 | Sprint 2 | CRITICAL | `property_state` from FTF API returns "FLORIDA" but SERVICE_STATE = "FL" — every FL order falsely flagged as out-of-state | dev_manager | CLOSED | 2026-05-26
I-051 | Sprint 2 | CRITICAL | Non-standard service types ("Land Survey Only", "Re-survey") pass through classifier unhandled — Pricing Engine fails with PricingError | dev_manager | CLOSED | 2026-05-26
I-052 | Sprint 2 | MAJOR | Building Stakeout orders not flagged — I-042 mandates human review but not implemented in code | dev_manager | CLOSED | 2026-05-26
I-053 | Sprint 2 | MAJOR | LLM classifier never enabled — classifier.txt stub unchanged since Sprint 2; Sprint 3 enrichment target missed | dev_manager | CLOSED | 2026-05-26
I-054 | Sprint 2 | MAJOR | NEVER_AUTO_QUOTE has 3 AI-added entries not confirmed by Robert — may be over-blocking auto-quotes | dev_manager | CLOSED | 2026-05-26
I-055 | Sprint 2 | MAJOR | B-II Title Review contradiction — I-004 (closed) says auto-quoteable; Robert (Recording 1) explicitly says human review required | dev_manager | CLOSED | 2026-05-26
I-056 | Sprint 3 | MAJOR | Teams approval buttons (potentialAction) empty — Robert/Mark have no UI to approve/reject from Teams; CLI-only is not production viable | dev_manager | CLOSED | 2026-05-26
I-057 | Sprint 2 | MAJOR | FTF `/pricing/overrides` endpoint not confirmed in API documentation — special_pricing orders may fail in staging | dev_manager | CLOSED | 2026-05-26
I-058 | Sprint 10 | MAJOR | No E2E integration test exists — all tests are unit tests with mocked dependencies | dev_manager | CLOSED | 2026-05-27
I-045 | Sprint 2 | MAJOR | Recording 02 Q1 — Full service type list in Generate Invoice dropdown not captured | dev_manager | OPEN | 2026-05-26
I-046 | Sprint 9 | MINOR | Recording 02 Q2 — All Track Flow order status values not fully confirmed | dev_manager | OPEN | 2026-05-26
I-047 | Sprint 5 | MAJOR | Recording 02 Q3 — County-specific pricing matrix undefined | dev_manager | CLOSED | 2026-05-27
I-048 | Sprint 3 | MAJOR | Recording 02 Q4 — "Smith Zone" yellow flag rule undefined | dev_manager | CLOSED | 2026-05-27
I-049 | Sprint 6 | MINOR | Recording 02 Q12 — No SLA defined for quote turnaround | dev_manager | OPEN | 2026-05-26
I-040 | Sprint 11 | MAJOR | 8 mid-pipeline order statuses not filterable via FTF API — On Hold, In-Field, Drafting Queue, etc. | dev_manager | CLOSED | 2026-05-27
I-041 | Sprint 2 | MAJOR | Competitor list pending — Robert confirmed it exists and will write it up | dev_manager | CLOSED | 2026-05-27
I-042 | Sprint 3 | MAJOR | Building Stakeout ambiguous — NGE "dabbling" in it again; treat as flag-for-human-review | dev_manager | CLOSED | 2026-05-27
I-043 | Sprint 6 | HIGH | Change order clause text needed — Ryan to draft; confirmed no existing text in estimates | dev_manager | CLOSED | 2026-05-27
I-006 | Sprint 7 | CRITICAL | Jessica recording (Recording 10) not yet conducted | dev_manager | CLOSED | 2026-05-27
I-007 | Sprint 8 | CRITICAL | Wyatt recording (Recording 11) not yet conducted | dev_manager | CLOSED | 2026-05-27
I-018 | Sprint 6 | MINOR | PII masking in logger.py covers email addresses only — phone numbers, property addresses, customer names logged in plain text | dev_manager | CLOSED | 2026-05-27
I-019 | Sprint 10 | MINOR | No prompt caching in claude_client.py — cost risk at scale with 7000+ Quote orders | dev_manager | OPEN | 2026-05-22
I-028 | Sprint 7 | MINOR | Agent 5 Reviewer must log both pre-correction and post-correction estimate for Sprint 7 demo | dev_manager | OPEN | 2026-05-22
I-032 | Sprint 8 | MAJOR | Recording 11 prerequisites — draft template + Excel vs PDF spec needed before recording | dev_manager | CLOSED | 2026-05-27
I-059 | Demo | MINOR | Demo narration: "50 new orders a week" too specific — change to "a lot of orders a week" for any client audience | dev_manager | CLOSED | 2026-05-26
I-060 | Demo | MINOR | Demo classify scene: "no competitor" text not explained — viewers confused why competitor is checked | dev_manager | CLOSED | 2026-05-26
I-061 | Sprint 5 | MAJOR | New agent required: monitor info@nexgensurveying.com for customer quote-approval emails → move quote to pending | dev_manager | CLOSED | 2026-05-27
I-062 | Sprint 6 | MAJOR | New feature: website chat → order conversion — customer says "go ahead" → AI asks address or order# → converts quote to pending | dev_manager | OPEN | 2026-05-26
I-063 | Sprint 7 | CRITICAL | Hard rule: refund requests must NEVER be processed by AI — always route to Jessica immediately, no further action | dev_manager | CLOSED | 2026-05-27
I-064 | Sprint 3 | MAJOR | Robert approval flow: hourly batch spreadsheet with Approve/Deny column — not per-order Teams ping | dev_manager | CLOSED | 2026-05-27
I-065 | Sprint 4 | MAJOR | Dynamic pricing factors not in current model: pools, wall count, sheds, driveways, distance from crew | dev_manager | CLOSED | 2026-05-27
I-066 | Sprint 5 | MAJOR | Historical invoicing: last 2 years of FTF invoice data needed as AI pricing reference | dev_manager | CLOSED | 2026-05-27
I-067 | Sprint 6 | MAJOR | AI training interface: Robert can describe jobs → AI stores pricing rationale for ongoing learning | dev_manager | CLOSED | 2026-05-27
I-068 | Sprint 5 | MAJOR | Florida PSM standards: feed FL Professional Surveyor and Mapper standards (Chapter 5J-17 FAC) to AI knowledge base | dev_manager | CLOSED | 2026-05-27
I-069 | Sprint 6 | MAJOR | Role-based AI modification: Jessica controls AR/refund rules, Robert controls pricing/logistics — cross-domain changes require both | dev_manager | CLOSED | 2026-05-27
I-070 | Future | MINOR | Weather monitoring agent: daily check → identify survey orders at risk of delay → draft proactive customer emails | dev_manager | OPEN | 2026-05-26
I-071 | Sprint 2 | MAJOR | "Table Survey" service type in FTF order form UI has no confirmed canonical mapping — will fall through to LLM normalization and may be misclassified | dev_manager | OPEN | 2026-05-27
I-072 | Sprint 2 | MINOR | "Elevation Code Only" UI label not in alias map — correctly maps to "Elevation Only" canonical | dev_manager | CLOSED | 2026-05-27
I-073 | Sprint 2 | MAJOR | FTF supports multiple child services per parent order — pipeline treats service_type as single value; multi-service orders may lose child services | dev_manager | OPEN | 2026-05-27
I-074 | Sprint 10 | MINOR | FTF API has no POST /customers endpoint — programmatic customer creation not possible; QA tests must use pre-existing customer_id | dev_manager | OPEN | 2026-05-27
CLOSED ISSUES (39)
ID | Sprint | Severity | Title | Resolved By | Closed
I-050 | Sprint 2 | CRITICAL | property_state FLORIDA vs FL normalization | dev_manager | 2026-05-26
I-051 | Sprint 2 | CRITICAL | Non-standard service types unhandled (Land Survey Only etc.) | dev_manager | 2026-05-26
I-052 | Sprint 2 | MAJOR | Building Stakeout not flagged (I-042 mandated) | dev_manager | 2026-05-26
I-053 | Sprint 2 | MAJOR | LLM classifier never enabled | dev_manager | 2026-05-26
I-056 | Sprint 3 | MAJOR | Teams approval buttons empty | prateek | 2026-05-26
I-001 | Sprint 2 | CRITICAL | Competitor names + domains list missing — Agent 4 flag logic incomplete | competitor_analyst | 2026-05-25
I-002 | Sprint 2 | CRITICAL | Never-auto-quote service list missing — Agent 4 flag trigger #2 incomplete | competitor_analyst | 2026-05-25
I-009 | Sprint 0 | CRITICAL | `db.get_pending_order()` used in sprint plan to check if order exists — function takes no args | dev_manager | 2026-05-21
I-010 | Sprint 0 | MINOR | `test_get_pricing_raises_pricing_error_on_failure` called `get_pricing()` without required `service` arg | dev_manager | 2026-05-21
I-011 | Sprint 0 | MINOR | `state.py` uses deprecated `datetime.datetime.utcnow()` — DeprecationWarning on Python 3.14 | dev_manager | 2026-05-21
I-012 | Sprint 1 | MAJOR | Monitor saved ALL FTF orders regardless of status — Delivered/Complete/Cancelled orders incorrectly queued | dev_manager | 2026-05-22
I-020 | Sprint 2 | MAJOR | ftf_client.py pagination silently returns empty list if API returns total=0 on first call | dev_manager | 2026-05-22
I-021 | Sprint 2 | MAJOR | logger.py dict-style record.args converted to string before masking — breaks dict-format log calls with TypeError | dev_manager | 2026-05-22
I-022 | Sprint 2 | MINOR | SERVICE_STATE = "FL" defined in both flag_triggers.py and settings.py — duplicate constant, one is dead code | dev_manager | 2026-05-22
I-014 | Sprint 2 | BLOCKER | Geocoding capability missing — no way to convert property_address to lat/lng for FEMA flood zone check | dev_manager | 2026-05-25
I-015 | Sprint 2 | CRITICAL | GET /orders/{id} individual order response schema unknown — may be only path to actual service_type | dev_manager | 2026-05-25
I-016 | Sprint 2 | CRITICAL | GET /customers/{id} response schema unknown — customer type (B2B/individual) and email field names unconfirmed | dev_manager | 2026-05-25
I-029 | Sprint 2 | MAJOR | Audit log (agent_decision_log) has no append-only access control — agents could overwrite prior records | dev_manager | 2026-05-25
I-034 | Sprint 3 | MAJOR | Monroe County flag trigger missing — Florida Keys orders need human review (non-standard pricing) | dev_manager | 2026-05-25
I-035 | Sprint 2 | MAJOR | VE coastal flood zone not flagged — elevation cert required but classifier missing this trigger | dev_manager | 2026-05-25
I-036 | Sprint 2 | MAJOR | Missing property_county not flagged — classifier cannot apply county-specific pricing rules | dev_manager | 2026-05-25
I-037 | Sprint 2 | MAJOR | property_lat outside Florida bounds not flagged — out-of-state lat/lng goes undetected when state field is blank | dev_manager | 2026-05-25
I-004 | Sprint 2 | MAJOR | B-II Title Review flag status unconfirmed | dev_manager | 2026-05-25
I-024 | Sprint 6 | MAJOR | Resend behavior for failed estimate emails undefined | dev_manager | 2026-05-25
I-027 | Sprint 2 | MAJOR | Pricing sync method undefined | dev_manager | 2026-05-25
I-030 | Sprint 7 | CRITICAL | 90-day AR escalation behavior ambiguous — auto-send to client or flag Jessica? | dev_manager | 2026-05-25
I-031 | Sprint 8 | MAJOR | No manual statement trigger defined — mid-month statement requests unhandled | dev_manager | 2026-05-25
I-033 | Sprint 2 | MAJOR | service_type="Quote" fallback strategy undefined | dev_manager | 2026-05-25
I-038 | Sprint 3 | MAJOR | Competitor list false-positive-risk entries + unconfirmed domains | dev_manager | 2026-05-25
I-039 | Sprint 2 | MAJOR | Service types in real orders not in 24-service list — unpriced custom CRM entries; "Land Survey Only" is high priority | dev_manager | 2026-05-25
I-013 | Sprint 11 | MAJOR | FTF API returns 207,622 orders but CRM shows 275,693 — 68,071 orders missing | dev_manager | 2026-05-25
I-044 | Sprint 6 | CRITICAL | AI pipeline design — Robert always reviews before sending; pipeline must be suggest-then-approve for ALL orders | prateek | 2026-05-26
I-017 | Sprint 2 | MAJOR | API rate limit on individual GET /orders/{id} calls — 500+ sequential calls per Classifier run | dev_manager | 2026-05-25
I-008 | Sprint 6 | MAJOR | Change order clause final Ryan approval before go-live | dev_manager | 2026-05-25
I-003 | Sprint 2 | CRITICAL | Construction/Permitting not in FTF pricing catalogue | dev_manager | 2026-05-25
I-023 | Sprint 3 | MINOR | Add CLI manual trigger for Agent 2 Monitor | dev_manager | 2026-05-25
I-025 | Sprint 3 | MAJOR | Approval inbound mechanism — Teams bot reads Robert/Mark chat replies; 24hr timeout escalates to Ryan + Wyatt | dev_manager | 2026-05-25
I-005 | Sprint 2 | MAJOR | Wetland Delineation — does NexGen perform this service? | dev_manager | 2026-05-25
I-026 | Sprint 4 | MAJOR | Change order clause — drafted, awaiting Ryan approval before Sprint 4 | dev_manager | 2026-05-25

## 📈 Data Insights
Production Invoice Analysis — May 2025 to May 2026 ¦ nexgen_ftf_db
Metric | Value | Metric | Value | Metric | Value
Total Invoiced | $13,205,323 | Total Records | 23,353
Unique Orders | ~18,497 | Avg Invoice | $565
AR Outstanding | $6,565,086 | Unpaid Rate | 35.9%
TOP SERVICES — Production Actuals
Service (CRM Label) | Orders | Total Revenue | Avg Price | Min | Max
Land Survey Only | 13260 | $8,170,826 | $616 | $0.01 | $35,000
Land Survey and Elevation | 5654 | $2,262,682 | $400 | $0.01 | $12,500
Quote (unclassified) | 1721 | $1,594,682 | $926 | $2 | $13,800
Boundary Survey | 992 | $563,055 | $567 | $50 | $10,000
Re-Survey / Update Survey | 406 | $161,475 | $397 | $0.01 | $2,800
Elevation Certificate | 365 | $99,190 | $271 | $0.01 | $1,500
ALTA Table A Survey | 16 | $81,200 | $5,075 | $1,500 | $12,500
Spot Survey (New client) | 106 | $62,500 | $589 | $350 | $2,500
Topography Survey | 61 | $29,525 | $484 | $75 | $1,800
COUNTY PRICING — Land Survey Only Actuals (n≥10)
County | Orders | Avg Price | Min | Max | Tier
OKEECHOBEE | 20 | $1,797 | $700 | $3,800 | Remote/Rural
HIGHLANDS | 35 | $1,337 | $575 | $5,000 | Remote/Rural
MARION | 77 | $1,052 | $300 | $5,000 | Remote/Rural
CITRUS | 37 | $954 | $475 | $4,800 | Remote/Rural
CLAY | 47 | $779 | $225 | $5,000 | North FL
POLK | 304 | $743 | $200 | $4,800 | Central FL
VOLUSIA | 92 | $734 | $250 | $4,500 | North FL
LAKE | 71 | $740 | $250 | $3,500 | Central FL
DUVAL | 175 | $654 | $200 | $4,800 | North FL
COLLIER | 225 | $643 | $200 | $3,800 | SW FL (Naples)
MARTIN | 284 | $631 | $200 | $4,800 | Treasure Coast
ORANGE | 213 | $607 | $200 | $4,500 | Central FL
PASCO | 350 | $608 | $200 | $4,800 | Central FL
INDIAN RIVER | 285 | $595 | $200 | $4,800 | Treasure Coast
CHARLOTTE | 234 | $591 | $250 | $4,800 | SW FL
MANATEE | 380 | $584 | $250 | $4,800 | Gulf Coast
HILLSBOROUGH | 680 | $575 | $200 | $4,800 | Central FL
PALM BEACH | 3310 | $571 | $200 | $5,000 | South FL
BREVARD | 347 | $560 | $200 | $4,800 | Space Coast
SARASOTA | 502 | $555 | $200 | $4,800 | Gulf Coast
MIAMI-DADE | 587 | $547 | $200 | $4,800 | South FL
HERNANDO | 199 | $540 | $275 | $4,400 | Central FL
PINELLAS | 418 | $527 | $200 | $3,500 | Gulf Coast
LEE | 947 | $500 | $225 | $4,800 | SW FL
BROWARD | 1398 | $512 | $200 | $5,000 | South FL
ST. LUCIE | 595 | $464 | $200 | $3,800 | Treasure Coast
SEMINOLE | 63 | $479 | $250 | $1,800 | Central FL
MONROE (Keys) | 35 | $1,735* | — | — | KEYS — Always flag
MONTHLY REVENUE TREND
Month | Orders Billed | Revenue
2025-05 | 415 | $209,995
2025-06 | 1803 | $998,687
2025-07 | 2090 | $1,165,817
2025-08 | 2020 | $1,136,098
2025-09 | 1944 | $1,100,770
2025-10 | 1990 | $1,208,782
2025-11 | 1564 | $899,195
2025-12 | 1724 | $1,061,520
2026-01 | 1657 | $1,016,150
2026-02 | 1723 | $950,890
2026-03 | 2219 | $1,217,541
2026-04 | 2212 | $1,304,785
2026-05 | 1692 | $941,167

## 🧪 QA Orders
QA Orders — NexGen Pipeline Test Scenarios
QA Order ID | Service Type | Customer Type | Flood Zone | Status | Notes
QA-TODAY-boundary-individual | Boundary Survey | individual | No | classified | Standard residential — clean path through pricing→writer→reviewer
QA-TODAY-boundary-flood | Boundary Survey | individual | Yes (AE) | classified | AE flood zone — elevation cert upcharge expected
QA-TODAY-topo-b2b | Topography Survey | b2b | No | classified | B2B topography — b2b pricing tier
QA-TODAY-final-survey | Final Survey | individual | No | classified | Final survey — Tampa-area residential
QA-TODAY-form-board | Form Board Survey | individual | No | classified | Form board — Jacksonville area
QA-TODAY-update-survey | Update Survey | individual | No | classified | Update survey — Gainesville area
QA-TODAY-elevation-cert-flagged | Elevation Certificate | individual | Yes (AE) | flagged | ALWAYS_FLAG — routes to human gate
QA-TODAY-alta-b2b-flagged | ALTA Table A Survey | b2b | No | flagged | ALWAYS_FLAG — human gate required
QA-TODAY-prateek-test-1 | Boundary Survey | individual | No | classified | Prateek Test 1 — FTF order 1000276115 (100 Test Lane, Orlando)
QA-TODAY-prateek-test-2 | Elevation Certificate | individual | Yes (AE) | flagged | Prateek Test 2 — FTF order 1000276116 (200 Test Blvd, Miami-Dade)
FTF Staging Orders Created: 1000276115 (Prateek Test 1) ¦ 1000276116 (Prateek Test 2) ¦ customer_id: 201911011657090565 ¦ status: Quote

## 🗂 Service Aliases
Service Type Alias Map — Production-Confirmed (2026-05-27)
CRM / FTF Label | Canonical Name | Prod Orders | Note
Land Survey Only | Boundary Survey | 12,119 | Most common — 57% of all orders
Land Survey and Elevation | Boundary Survey (bundle) | 2,878 | Includes EC; price varies
Property Survey and Elevation | Boundary Survey (bundle) | 65 | Same as above
Re-Survey | Update Survey | 391 | Confirmed from prod data
Resurvey / Resurvey (trailing space) | Update Survey | 2
Spot Survey (New client) | Foundation Tie-In | 106 | First-time client
Spot Survey (Prior NexGen Survey) | Foundation Tie-In | 3 | Return client
CAD file / CAD | Survey Re-draw | 72+29 | Fixed $250 add-on
Construction Survey | Topography Survey | 1
Construction Survey Update | Topography Survey | 5 | Topo update
Topo Survey / Topographic Survey | Topography Survey | confirmed
Update/Topo | Update Survey or Topography | 2 | Context-dependent
As-Built Survey | Final Survey | 1
Lot split Survey | Lot Split | 4
Re-Flag Corners | Property Flagging | 2
Line Stake Out / Offset Staking | Building Stake Out | 2+1
Elevation Code Only | Elevation Only | FTF UI label | I-072 fixed
Elevation Cert | Elevation Certificate | alias
ALTA Survey / ALTA Conversion / Optional ALTA Table A | ALTA Table A Survey | confirmed
Abstract survey (includes B-II review) | B-II Title Review | 1
Finished Floor Elevation on Survey | Elevation Certificate | 1 | Add-on
Add topo to existing survey | Topography Survey | 1
Topo upgrade | Topography Survey | 1
Quote | ⚠️ UNCLASSIFIED — flag | 2,135 | Human must identify service
Table Survey | ❓ UNKNOWN — I-071 open | — | Not confirmed by Robert
Expedited Rush Survey | ⚠️ FLAG — surcharge needed | 1
Cancel after office prep (10%) | ⚠️ CANCELLATION billing | 2 | Partial billing
Cancel after field work (50%) | ⚠️ CANCELLATION billing | 1 | Partial billing